## Complete Sprint Plan
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Assignee | Status | Tools / Technologies Used | Remarks
S1 | S1 | US-001 | Introduction to project and problem understanding (Log analytics use case) | MUST HAVE | G Avinash | 3-completed | No dependency | Initial understanding completed
S1 | S1 | US-001 | Define project objectives and workflow for log analytics engine | MUST HAVE | G Avinash | 3-completed | Lucid chart | Objectives finalized
S2 | S2 | US-001 | Research log processing techniques and anomaly detection approaches | MUST HAVE | G Avinash | 3-completed | online docs/blog | Approach finalized
S2 | S2 | US-001 | Design system architecture and module separation | MUST HAVE | G Avinash | 3-completed | Lucid chart | Modules defined
S3 | S3 | US-001 | Implement log ingestion from CSV and simulated real-time source | MUST HAVE | G Avinash | 3-completed | python | Log ingestion working
S3 | S3 | US-001 | Implement log processing pipeline with filtering and aggregation | MUST HAVE | G Avinash | 3-completed | pandas, dask | Pipeline functional
S4 | S4 | US-001 | Implement time-based aggregation for error logs | MUST HAVE | G Avinash | 3-completed | pandas, dask | Aggregation verified
S4 | S4 | US-001 | Implement Z-score based anomaly detection logic | MUST HAVE | G Avinash | 3-completed | statistical logic | Anomaly detection accurate
S5 | S5 | US-001 | Build interactive dashboard for log visualization | MUST HAVE | G Avinash | 3-completed | streamlit | Dashboard created
S5 | S5 | US-001 | Integrate Plotly charts for anomaly visualization | SHOULD HAVE | G Avinash | 3-completed | plotly | Charts integrated
S6 | S6 | US-001 | Integrate log generator, processing pipeline, and dashboard | MUST HAVE | G Avinash | 3-completed | Vs code | End-to-end flow working
S6 | S6 | US-001 | Perform functional testing and fix import/dependency issues | MUST HAVE | G Avinash | 3-completed | Local testing | System stable
S7 | S7 | US-001 | Prepare project for cloud deployment | MUST HAVE | G Avinash | 3-completed | github | Deployment ready
S7 | S7 | US-001 | Deploy Streamlit application on Render cloud | MUST HAVE | G Avinash | 3-completed | Render cloud | Successfully deployed